## Workproducts
ReleaseID | PhaseID | TeamID | WorkProductID | WorkProductName | Responsible | Accountable | Consulted | Informed | Status
R1 | Ph1 | T1 | WP_R1T1 | Business Requirements
R1 | Ph1 | T1 | WP_R1T1 | High Level Design
R1 | Ph2 | T1 | WP_R1T1 | Detailed Design
R1 | Ph2 | T2 | WP_R1T2 | Detailed Plans
R1 | Ph3 | T2 | WP_R1T2 | Implementation Plan
R1 | Ph2 | T2 | WP_R1T2 | Code
R1 | Ph3 | T2 | WP_R1T2 | Test Results
R1 | Ph1 | T3 | WP_R1T3 | Test Data
R1 | Ph1 | T4 | WP_R1T4 | Test Strategy
R1 | Ph2 | T4 | WP_R1T4 | Test Plan
R1 | Ph3 | T4 | WP_R1T4 | Test Summary Report
R1 | Ph1 | T5 | WP_R1T5 | Deployment Plan
R1 | Ph2 | T5 | WP_R1T5 | Training Plan
R1 | Ph2 | T5 | WP_R1T5 | Change Plan
R1 | Ph3 | T5 | WP_R1T5 | Cutover Report
R2 | Ph1 | T1 | WP_R2T1 | Business Requirements
R2 | Ph1 | T1 | WP_R2T1 | High Level Design
R2 | Ph2 | T1 | WP_R2T1 | Detailed Design
R2 | Ph2 | T2 | WP_R2T2 | Interface Design
R2 | Ph3 | T3 | WP_R2T3 | Implementation Plan
R2 | Ph2 | T3 | WP_R2T3 | Code
R2 | Ph3 | T4 | WP_R2T4 | Test Results
R2 | Ph1 | T4 | WP_R2T4 | Test Strategy
R2 | Ph1 | T5 | WP_R2T5 | Deployment Plan
R2 | Ph2 | T5 | WP_R2T5 | Training Plan
R2 | Ph3 | T3 | WP_R2T3 | Test Results
R2 | Ph1 | T3 | WP_R2T3 | Interface Design
R2 | Ph2 | T4 | WP_R2T4 | Test Plan
R2 | Ph2 | T4 | WP_R2T4 | Test Summary Report
R2 | Ph3 | T5 | WP_R2T5 | Cutover Report

## Teams
TeamID | TeamName | TeamLead
T1 | Design | Team Lead 1
T2 | Internal Development | Team Lead 2
T3 | Vendor XYZ | Team Lead 3
T4 | E2E Testing | Team Lead 4
T5 | Deployment | Team Lead 5

## Releases
ReleaseID | ReleaseName | ReleaseLead
R1 | Release 1 | Release 1 Name
R2 | Release 2 | Release 2 Name

## Phases
PhaseID | PhaseName | PhaseDescription
Ph1 | Design/Build
Ph2 | Test
Ph3 | Deployment

## Activities
ActivitiyID | ActivityName | ActivityDescription | ActivityDefaultDaysDuration | ActivitySequence
A1 | Create Initial Draft |  | 5 | 1
A2 | Review |  | 1 | 2
A3 | Rework |  | 3 | 3
A4 | Final Review |  | 1 | 4
A5 | Approval |  | 0 | 5